## Open Items
ENGINEERING REGULATORS' PRESIDENTS' GROUP MEETING
ACTION REGISTER
TRACKING # | ITEM DETAILS | DATE OPENED (Meeting Date) | OPENED BY | DUE DATE | COMMENTS | ACTIONED BY | COMMENT | Status | DATE CLOSED
20160223-003 | Regarding Board member orientation. It was discussed that a one-pager Regulator’s Orientation was sent out, but is not as effective because it is passive and up to the Regulators’ Presidents to interpret meaning. It was discussed that Engineers Canada might prepare and provide orientation at these meetings, including a roster of who is rotating when (Presidents and Vice-Presidents/Presidents-Elect). It may be impacted by the new Terms of Reference that are being proposed by the Task Force at that meeting. | 2016-02-23 | G. Strong | 2017-02-28 | Updated PPT Draft for consideration | C. Brown | EC Staff to present onboarding draft to be updated as per comments from Sept/2016 meeting | Open
20160223-009 | Engineers Canada to collect the data on how the mobility agreement is being implemented by each association. Tabulated summary of the information to be circulated to the Presidents. | 2016-02-23 | D. Jayas | 2016-05-26 |  | J. Ricci | To be sent. | Open
20160223-010 | BC to provide a copy of the Joint Registration document being used by PEI, BC and Nova Scotia. Put this on the Agenda for review and discussion in May. | 2016-02-23 | L. McFarlane | 2016-05-26 |  | C.Brown | Send copy to all Presidents | Open
20160223-016 | Ask Engineers Canada to gather data on current ethics training by each Association/University (ie Iron Pin) and report back to Presidents meeting. | 2016-05-26 | C.Roney | ASAP |  | C. Roney |  | Open
20160927-001 | C. Roney to to submit one page summary on ethics training | 2016-09-27 | M. Wrinch | Next meeting |  | C.Brown |  | Open
20160927-002 | Produce what are the differences (a table) of what the different registration methods are from various provinces and compare so that associations can see and collaborate on national harmony. | 2016-09-27 | M. Wrinch | Next meeting |  | C.Brown |  | Open
20160927-003 | Follow-up on progress regarding finanical reporting of prospectus reports. There was an issue with CA S (you) who wanted to know more about how protects and actions are being delivered on with budgets included. | 2016-09-27 | M. Wrinch | Next meeting |  | C.Brown |  | Open
20160927-004 | It was suggested that all processing for assessments should be the same and done by the regulators and not by Engineers Canada. A consensus by the group to flag or produce what the differences are of the registration methods from various provinces and to compare these so that the regulators can see and collaborate to attain national harmony. | 2016-09-27 | T. Zrymiak | Next meeting |  | All (Presidents) |  | Open
20160927-005 | Update on status of a report on the different mobility practices across the country, and who now has responsibility for this report. ACTION: this was asked a few times over the year, there may be material available at APEG BC or provide a simplified table for the group to review . | 2016-09-27 | C. Brown | Next meeting |  | C. Brown | Reference above: 20160223-009 | Open
20160927-006 | Summary from C. Roney to be circulated. (on a high-level outlook, EC delivers to the regulators, the Accreditation Board, and the QB. On a National Level, national presentation work with federal government seeking our advice on matters involving engineering. The list of what EC's priorities are were discussed). | 2016-09-27 | C. Roney | Next meeting |  | EC |  | Open
20160927-007 | Forward K. Allen's letter on ISO initiative to redefine the term "risk" to which EC responded. There was a considerable amount of discussion around the term "risk". Not necessarily a "negative" term. Action: The group would like to hear the follow-up on the topic if there is any. | 2016-09-27 | M. Wrinch | Next meeting |  | C. Brown |  | Open
20160927-008 | Presidents are encouraged to approach the Board Members who are appointed by them and have this conversation since the Board works for the Regulators. | 2016-09-27 | C. Zinck | Next meeting |  | All (Presidents) |  | Open

## Closed Items
ENGINEERING REGULATORS' PRESIDENTS' GROUP MEETING
ACTION REGISTER
TRACKING # | ITEM DETAILS | DATE OPENED (Meeting Date) | OPENED BY | DUE DATE | COMMENTS | ACTIONED BY | COMMENT | Status | DATE CLOSED
20160223-001 | The Synergy Task Force from 6 years ago should be distributed to the Presidents' Group and put on the Agenda for next meeting. | 2016-02-23 | L. McFarlane | ASAP | Included with the February 23, 2016 Minutes | L. McFarlane |  | Closed | 2016-02-23
20160223-002 | To have a Presidents' Meeting Action Register created and updated for all meetings. Task Force consists of: J. Proulx, M. Wrinch and M.-A. Hodges. | 2016-02-23 | J. Proulx | 26-MAY2-2016 | Included with the February 23, 2016 Minutes | D. Smith | For approval | Closed | 2016-05-26
20160223-004 | For all Regulators’ Presidents to gather input on what is important to them and provide it to Engineers Canada by May 12, 2016. In turn, this information will be fed directly to the Board Workshop in June 2016. If these inputs are obtained before the May meeting, Engineers Canada will assist by compiling them into one document, which will be placed on the May agenda for a brief discussion of the findings of the compiled document. | 2016-02-23 | C. Roney | 2016-05-12 | To be discussed further at the May 26, 2016 AGM. | Regulators' Presidents | for comment | Closed
20160223-005 | Send Engineers Canada CPD Guidelines for Regulators to Presidents for their review and awareness. | 2016-02-23 | D. Jayas | 2016-04-07 | Included with the February 23, 2016 Minutes | D. Smith |  | Closed | 2016-05-26
20160223-006 | Discussed that there should be a projector for all future meetings, as it would be helpful for presenting information. | 2016-02-23 | M. Wrinch | On-going |  | D. Smith |  | Closed | 2016-05-26
20160223-007 | APEGBC - M. Wrinch will provide a copy of the presentation (APEGBC’s OQM system nation-wide) to all Regulator Presidents. | 2016-02-23 | M. Wrinch | 2016-04-07 | Included with the February 23, 2016 Minutes | D. Smith |  | closed
20160223-008 | APEGBC will put together a “How to Implement OQM” presentation/package and send to Colin/Daphne for distribution to all Regulator Presidents. | 2016-02-23 | M. Wrinch | 2016-05-26 |  | M. Wrinch |  | closed
20160223-011 | Manitoba to send out process of the academic review that they are using. | 2016-02-23 | L. McFarlane | ASAP | Included with the February 23, 2016 Minutes | L. McFarlane |  | Closed
20160223-012 | D. Jayas to confirm if the National Code of Ethics has been completed. | 2016-02-23 | D. Jayas | ASAP |  | D. Jayas |  | Closed
20160223-013 | Engineering Regulators' Presidents' Group are all asked to provide a short (3-5 minute) presentation at the AGM in May in Charlottetown. | 2016-02-23 | L. McFarlane | ASAP | Template will be emailed by Kim Allen, CEO, Engineers Canada, under separate cover. | Regulators' Presidents |  | Closed | 2016-05-26
20160223-014 | Engineering Regulators' Presidents' items for AGM are due two weeks prior to the AGM. | 2016-02-23 | L. McFarlane | 2016-05-12 |  | Regulators' Presidents | Done | Closed | 2016-05-26
20160223-015 | For Colin/Daphne to locate the Presidents’ Folder that is mentioned in the Terms of Reference and advise as to its location. Post updated TOR on Engineers Canada website | 2016-02-23 | C. Brown | 2016-05-26 |  | C. Brown | Location will be communicated to group. | closed
20160526-017 | C. Brown to foward information to A. Dietrich (APEGNB) and take care of mobility information. | 2016-05-26 | C. Brown | ASAP |  | C. Brown |  | Closed
20150526-018 | M. Wrinch confirmed the first version of the Action Register will be out before the September meeting. | 2016-05-26 | M. Wrinch | September 20, 2016 |  |  |  | closed